## QA Team Breakup
QA Team Breakup
Environment | Team Defination | Team members | Tasks Details | QA Reviewer
QA | Functional Team | Junior - 4 Resource + Senior -1 Resource | 1. Understand requirement and TCs writing : 16 day 2. Functional testing : 24 days 3. Regression Testing: 10 days | QA Lead
| Non Functional Team | Junior - 2 Resource + Senior - 1 Resource | 1. UI Automation - Script writing and execution: 46 days 2. Performance Automation - Script writing and execution: 7 days | QA Lead
Staging | Functional Team | Junior - 4 Resource + Senior -1 Resource | 1. Sanity testing for all modules- 4 day 2. Retesting of fixes if any - 2 days | QA Lead
| Non Functional Team | Junior - 2 Resource + Senior - 1 Resource | 1. Performance test script execution: 2 day 2. UI Automation script execution: 3 day | QA Lead
Production | Functional Team | Junior - 4 Resource + Senior -1 Resource | 1. Sanity testing for all modules: 1 day | QA Lead

## Functional Testing Milestones
Milestones | Sprint Dates | Items | Dev Start Date | Dev End Date | QA Start Date | QA End Date | Comments
Sprint-1 | 14th Aug -25th Aug | TestCases writing for Login screen with Authorization and Dashboard | NA | NA | 2023-08-14 | 2023-08-18
|  | Login Screen and loading basic Dashboard Including Email ID Authorization and Google Authentication/Social Login | 2023-08-14 | 2023-08-18 | 2023-08-21 | 2023-08-24
|  | Dev Analysis of Accounts and Contracts Page Functionality | 2023-08-21 | 2023-08-24 | NA | NA
Sprint-2 | 28th Aug - 8th Sept | TestCases writing for Accounts and Contracts Page | NA | NA | 2023-08-28 | 2023-08-31
|  | Accounts Page Functionality | 2023-08-28 | 2023-08-31 | 2023-09-01 | 2023-09-04
|  | Contracts Page Functionality | 2023-09-01 | 2023-09-04 | 2023-09-05 | 2023-09-08
|  | Dev Analysis of Reports and Admin Page Functionality | 2023-09-05 | 2023-09-08 | NA | NA
Sprint-3 | 11th Sept -22nd Sept | TestCases writing for Accounts and Admin Page | NA | NA | 2023-09-11 | 2023-09-14
|  | Reports Page Functionality | 2023-09-11 | 2023-09-14 | 2023-09-15 | 2023-09-19
|  | Admin Page Functionality | 2023-09-15 | 2023-09-18 | 2023-09-20 | 2023-09-22
|  | Dev Analysis of Bug reported in Drop1 and Drop2 | 2023-09-19 | 2023-09-22 | NA | NA
Sprint-4 | 25th Sept -6th Oct | Regression TCs writing | NA | NA | 2023-09-25 | 2023-09-28
|  | QA Regression | NA | NA | 2023-09-28 | 2023-10-04
|  | Functional Bug Fixes of Drop 1 and Drop 2 | 2023-09-28 | 2023-10-03 | 2023-10-05 | 2023-10-06
|  | Dev Analysis of Bug reported in Drop3 | 2023-10-04 | 2023-10-06 | NA | NA
Sprint-5 | 9th Oct - 20th Oct | Regression Fixes | 2023-10-09 | 2023-10-12 | 2023-10-12 | 2023-10-15
|  | Functional Bug Fixes of Drop 3 | 2023-10-13 | 2023-10-15 | 2023-10-16 | 2023-10-20
Sprint-6 | 23rd Oct - 4th Nov | Staging Environment Stability | 2023-10-26 | 2023-10-27 | 2023-10-23 | 2023-10-26
|  | Retesting of issues | NA | NA | 2023-10-28 | 2023-10-29
|  | UAT | NA | NA | NA | NA | 1-Nov to 3-Nov : UAT from Client
|  | Production Release | 2023-11-04 | 2023-11-04 | 2023-11-04 | 2023-11-04 | 04-Nov : Release to Production Sanity and Stabilization to be done on same day

## Automation Testing MileStones
Milestones | Sprint Dates | Items | QA Start Date | QA End Date
Sprint-1 | 14th Aug -25th Aug | Framework Design and Peer Review | 2023-08-14 | 2023-08-22
|  | Base Class creation | 2023-08-23 | 2023-08-25
Sprint-2 | 28th Aug - 8th Sept | Login Page TCs to be automated - Finalize | 2023-08-28 | 2023-08-29
|  | Login Page TCs Automation | 2023-08-30 | 2023-09-04
|  | Accounts Page TCs to be automated - Finalize | 2023-09-05 | 2023-09-06
|  | Contracts Page TCs to be automated - Finalize | 2023-09-07 | 2023-09-08
Sprint-3 | 11th Sept -22nd Sept | Accounts Page TCs Automation | 2023-09-11 | 2023-09-14
|  | Contracts Page TCs Automation | 2023-09-15 | 2023-09-18
|  | Reports Page TCs to be automated - Finalize | 2023-09-19 | 2023-09-20
|  | Admin Page TCs to be automated - Finalize | 2023-09-21 | 2023-09-22
Sprint-4 | 25th Sept -6th Oct | Reports Page TCs Automation | 2023-09-25 | 2023-09-27
|  | Admin Page TCs Automation | 2023-09-28 | 2023-10-02
|  | Regression TCs to be automated- Finalize | 2023-10-03 | 2023-10-06
Sprint-5 | 9th Oct - 20th Oct | Regression TCs Automation | 2023-10-09 | 2023-10-16
|  | Performance Script Design and Execution- Drop 1 | 2023-10-17 | 2023-10-20
Sprint-6 | 23rd Oct - 4th Nov | Performance Script Design and Execution- Drop 2 | 2023-10-23 | 2023-10-25
|  | UI Automation Script running in Staging | 2023-10-26 | 2023-10-30
|  | Performance Script running in Staging | 2023-10-31 | 2023-11-01